## Sheet1
			Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8	Week 9	Week 10
Pre-study	Find relevant theory		x
	Read theory		x	x
	delimit study from theory			x
write introduction				x
write background				x
write theory					x	x	x	x
write method								x	x	x	x
implementations											x	x

			Week 11	Week 12	Week 13	Week 14	Week 15	Week 16	Week 17	Week 18	Week 19	Week 20
Mid-thesis review			x
implementations			x	x	x	x
testing						x	x	x
summary of results								x	x
write results and conclusions								x	x
proof reading									x	x	x
write reflection document												x
final presentation												x

	Risks:
	Does not get time at NSC to do tests
	Much time spent on debugging