## Sheet1
			Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8	Week 9	Week 10
Pre-study	Find relevant theory		x
	Read theory		x	x
	delimit study from theory			x
write introduction				x	x
write background				x	x
write theory					x	x	x	x	x
write method									x	x	x	x
implementations												x

			Week 11	Week 12	Week 13	Week 14	Week 15	Week 16	Week 17	Week 18	Week 19	Week 20
Mid-thesis review			x
implementations			x	x	x	x
testing						x	x	x
summary of results								x	x
write results and conclusions								x	x
proof reading									x	x	x
write reflection document												x
final presentation												x

	Risks:
	Does not get time at NSC to do tests
	Much time spent on debugging
	time planning is incorrect
	underestimate the complexity of the problem
	Not enough literature about the subject
	No one to get help from if I get stuck